## Main
| No Projs | 3 | got
GIT Benefits Stage | Look ahead | 4 | Togo
| Level | 2 | Benue
| Path | C:\Users\Julian\OneDrive\Documents\OneSheet\titilayo ilesanmi\Planning template v3.0.mpp
Import
Look Ahead Report
Generate
4 Weeks
12 Weeks
1
2
3
4
Export to PPT

## got
Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | Last RAG | RAG | Issue | Impact | Action
|  | Business Milestones | [8 empty] | All
| 0 | No Tasks
|  | Concept | [8 empty] | All
| 0 | No Tasks
|  | Define | [8 empty] | All
| 0 | No Tasks
|  | Develop | [8 empty] | All
GREEN-10.5 | 1 | Develop Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | got
GREEN-11 | 1 | Design Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | got
GREEN-11.5 | 1 | Full Requirements Definition Signed Off | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | got
GREEN-12 | 1 | Mid Level Platform Designs Complete | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | got
GREEN-12.5 | 1 | <Test Phase> Environment and Data Ready for Testing | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | got
GREEN-13 | 0 | Design Complete | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | got
|  | Deploy | [8 empty] | All
| 0 | No Tasks
|  | Benefits | [8 empty] | All
| 0 | No Tasks
|  | Group IT Milestones | [8 empty] | All
| 0 | No Tasks
|  | GIT Define Stage | [8 empty] | All
| 0 | No Tasks
|  | GIT Develop Stage | [8 empty] | All
| 0 | No Tasks
|  | GIT Deploy Stage | [8 empty] | All
| 0 | No Tasks
|  | GIT Benefits Stage | [8 empty] | All

## Togo
Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | Last RAG | RAG | Issue | Impact | Action
|  | Business Milestones | [8 empty] | All
| 0 | No Tasks
|  | Concept | [8 empty] | All
| 0 | No Tasks
|  | Define | [8 empty] | All
| 0 | No Tasks
|  | Develop | [8 empty] | All
GREEN-14 | 1 | Build Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
GREEN-14.5 | 0 | Build Complete | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
GREEN-15 | 1 | Test Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-15.1 | 1 | System Test Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-15.2 | 0 | System Test Complete | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-15.3 | 1 | GIT Change Slot Requested | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-15.4 | 1 | System Integration Test Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-15.5 | 0 | System Integration Test Complete | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-15.6 | 1 | User Acceptance Test Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-15.7 | 0 | User Acceptance Test Complete | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-15.8 | 1 | Non-Functional Test Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-15.9 | 0 | Non-Functional Test Complete | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-16.5 | 0 | Test Complete | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-17 | 1 | Develop Complete | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
|  | Deploy | [8 empty] | All
-18 | 1 | Deploy Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-18.1 | 0 | Deployment Start | 2020-05-01 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-18.5 | 0 | Deployment Live | 2020-05-08 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-18.6 | 0 | People Impacts Delivered | 2020-05-08 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-18.7 | 0 | Customer Impacts Delivered | 2020-05-08 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-19 | 1 | Post Implementation Review Signed Off | 2020-05-08 | 2020-06-05 | 1421.875 |  | RED |  |  |  | Togo
-20.5 | 1 | Handover Report Signed Off | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Togo
-21 | 1 | Deploy Complete | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Togo
|  | Benefits | [8 empty] | All
-22 | 1 | Benefits Realisation Start | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Togo
-24 | 1 | Benefits Realisation Complete/Project Closed | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Togo
|  | Group IT Milestones | [8 empty] | All
| 0 | No Tasks
|  | GIT Define Stage | [8 empty] | All
-90000 | 1 | GIT Engagement Start | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Togo
-90001 | 0 | GIT Engagement End (IT Readiness Assessment 2.1 signed off) | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Togo
-90002 | 1 | GIT Investigation Start | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Togo
|  | GIT Develop Stage | [8 empty] | All
| 0 | No Tasks
|  | GIT Deploy Stage | [8 empty] | All
| 0 | No Tasks
|  | GIT Benefits Stage | [8 empty] | All

## Benue
Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | Last RAG | RAG | Issue | Impact | Action
|  | Business Milestones | [8 empty] | All
| 0 | No Tasks
|  | Concept | [8 empty] | All
| 0 | No Tasks
|  | Define | [8 empty] | All
| 0 | No Tasks
|  | Develop | [8 empty] | All
| 0 | No Tasks
|  | Deploy | [8 empty] | All
| 0 | No Tasks
|  | Benefits | [8 empty] | All
| 0 | No Tasks
|  | Group IT Milestones | [8 empty] | All
| 0 | No Tasks
|  | GIT Define Stage | [8 empty] | All
-499-251 | 0 | Method of Service Introduction Agreed (i.e. V&E Managed / Project Managed/ Change Managed), SI Acceptance Area Representatives Engaged | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Benue
-90003 | 0 | GIT Investigation End (IT Readiness Assessment 2.2 signed off) | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Benue
|  | GIT Develop Stage | [8 empty] | All
-90003.5 | 0 | GIT Develop Start | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Benue
-90004 | 1 | GIT Design Start | 2020-05-08 | 2020-05-29 | 1417.5 |  | RED |  |  |  | Benue
|  | GIT Deploy Stage | [8 empty] | All
| 0 | No Tasks
|  | GIT Benefits Stage | [8 empty] | All