## Task View
Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | Last RAG | RAG | Issue | Impact | Action
Business Milestones
Concept
GREEN-0.5 | 1 | Concept Start | NA | 2014-01-02 | DTI |  | GREEN
GREEN-1.5 | 1 | Project Brief Complete | NA | 2014-01-02 | DTI |  | GREEN
GREEN-2 | 1 | Concept Complete | NA | 2014-01-02 | DTI |  | GREEN
Define
GREEN-3 | 1 | Define Start | NA | 2014-01-02 | DTI |  | GREEN
GREEN-4.5 | 0 | Initial Funding Request Approved | NA | 2014-01-02 | DTI |  | GREEN
GREEN-6.5 | 1 | Initial Requirements Definition Signed Off | NA | 2014-01-02 | DTI |  | GREEN
GREEN-7 | 1 | Test Data Strategy Complete | NA | 2014-01-02 | DTI |  | GREEN
GREEN-7.5 | 1 | Test Environment Strategy Complete | NA | 2014-01-02 | DTI |  | GREEN
GREEN-8 | 1 | Solution Feasibility Report Signed Off | NA | 2014-01-02 | DTI |  | GREEN
GREEN-8.1 | 1 | Group Compliance Checks Complete | NA | 2014-01-02 | DTI |  | GREEN
GREEN-8.5 | 1 | CSOC Impact Assessment Complete | NA | 2014-01-02 | DTI |  | GREEN
GREEN-9 | 1 | PSOC Impact Assessment Complete | NA | 2014-01-02 | DTI |  | GREEN
GREEN-10 | 0 | Define Complete | NA | 2014-01-02 | DTI |  | GREEN
Develop
GREEN-10.5 | 1 | Develop Start | NA | 2014-01-02 | DTI |  | GREEN
GREEN-11 | 1 | Design Start | NA | 2014-01-02 | DTI |  | GREEN
GREEN-11.5 | 1 | Full Requirements Definition Signed Off | NA | 2014-01-02 | DTI |  | GREEN
GREEN-12 | 1 | Mid Level Platform Designs Complete | NA | 2014-01-02 | DTI |  | GREEN
GREEN-12.5 | 1 | <Test Phase> Environment and Data Ready for Testing | NA | 2014-01-02 | DTI |  | GREEN
GREEN-13 | 0 | Design Complete | NA | 2014-01-02 | DTI |  | GREEN
GREEN-14 | 1 | Build Start | NA | 2014-01-02 | DTI |  | GREEN
GREEN-14.5 | 0 | Build Complete | NA | 2014-01-02 | DTI |  | GREEN
GREEN-15 | 1 | Test Start | NA | 2014-01-02 | DTI |  | GREEN
-15.1 | 1 | System Test Start | NA | 2014-01-02 | DTI |  | GREEN
-15.2 | 0 | System Test Complete | NA | 2014-01-02 | DTI |  | GREEN
-15.3 | 1 | GIT Change Slot Requested | NA | 2014-01-02 | DTI |  | GREEN
-15.4 | 1 | System Integration Test Start | NA | 2014-01-02 | DTI |  | GREEN
-15.5 | 0 | System Integration Test Complete | NA | 2014-01-02 | DTI |  | GREEN
-15.6 | 1 | User Acceptance Test Start | NA | 2014-01-02 | DTI |  | GREEN
-15.7 | 0 | User Acceptance Test Complete | NA | 2014-01-02 | DTI |  | GREEN
-15.8 | 1 | Non-Functional Test Start | NA | 2014-01-02 | DTI |  | GREEN
-15.9 | 0 | Non-Functional Test Complete | NA | 2014-01-02 | DTI |  | GREEN
-16.5 | 0 | Test Complete | NA | 2014-01-02 | DTI |  | GREEN
-17 | 1 | Develop Complete | NA | 2014-01-02 | DTI |  | GREEN
Deploy
-18 | 1 | Deploy Start | NA | 2014-01-02 | DTI |  | GREEN
-18.1 | 0 | Deployment Start | NA | 2014-01-02 | DTI |  | GREEN
-18.5 | 0 | Deployment Live | NA | 2014-01-02 | DTI |  | GREEN
-18.6 | 0 | People Impacts Delivered | NA | 2014-01-02 | DTI |  | GREEN
-18.7 | 0 | Customer Impacts Delivered | NA | 2014-01-02 | DTI |  | GREEN
-19 | 1 | Post Implementation Review Signed Off | NA | 2014-01-02 | DTI |  | GREEN
-20.5 | 1 | Handover Report Signed Off | NA | 2014-01-02 | DTI |  | GREEN
-21 | 1 | Deploy Complete | NA | 2014-01-02 | DTI |  | GREEN
Benefits
-22 | 1 | Benefits Realisation Start | NA | 2014-01-02 | DTI |  | GREEN
-24 | 1 | Benefits Realisation Complete/Project Closed | NA | 2014-01-02 | DTI |  | GREEN
Group IT Milestones
GIT Define Stage
-90000 | 1 | GIT Engagement Start | NA | 2014-01-02 | DTI |  | GREEN
-499-234 | 4 | Raise SI Workflow Record | NA | 2014-01-02 | DTI |  | GREEN
-800 | 4 | Project Definition Workshop held | NA | 2014-01-02 | DTI |  | GREEN
-805 | 4 | Master Work Order created | NA | 2014-01-02 | DTI |  | GREEN
-810 | 4 | Scope Specification completed | NA | 2014-01-02 | DTI |  | GREEN
-499-238 | 4 | Architecture Overview completed | NA | 2014-01-02 | DTI |  | GREEN
-499-239 | 4 | Deliverable Review List updated | NA | 2014-01-02 | DTI |  | GREEN
-499-240 | 4 | IT Project Management Plan completed | NA | 2014-01-02 | DTI |  | GREEN
-820 | 4 | IT Finance Workbook & Investment Appraisal Template signed off | NA | 2014-01-02 | DTI |  | GREEN
-90001 | 0 | GIT Engagement End (IT Readiness Assessment 2.1 signed off) | NA | 2014-01-02 | DTI |  | GREEN
-90002 | 1 | GIT Investigation Start | NA | 2014-01-02 | DTI |  | GREEN
-499-244 | 4 | Master Work Order - request for quotation issued | NA | 2014-01-02 | DTI |  | GREEN
-499-245 | 4 | Implementation Plan drafted | NA | 2014-01-02 | DTI |  | GREEN
-835 | 4 | Master Test Plan created | NA | 2014-01-02 | DTI |  | GREEN
-499-247 | 4 | SOX Impact Assessment submitted | NA | 2014-01-02 | DTI |  | GREEN
-845 | 4 | Mid Level Platform Design baselined | NA | 2014-01-02 | DTI |  | GREEN
-850 | 4 | Initial Requirements Specification signed off | NA | 2014-01-02 | DTI |  | GREEN
-499-250 | 4 | Infrastructure Design Review completed | NA | 2014-01-02 | DTI |  | GREEN
-499-251 | 0 | Method of Service Introduction Agreed (i.e. V&E Managed / Project Managed/ Change Managed), SI Acceptance Area Representatives Engaged | NA | 2014-01-02 | DTI |  | GREEN
-851 | 4 | Non-Functional Engineering Risk Assessment | NA | 2014-01-02 | DTI |  | GREEN
-499-253 | 4 | SOX ATP (KC2) submitted | NA | 2014-01-02 | DTI |  | GREEN
-499-254 | 4 | SI Acceptance Area Representatives Engaged | NA | 2014-01-02 | DTI |  | GREEN
-90003 | 0 | GIT Investigation End (IT Readiness Assessment 2.2 signed off) | NA | 2014-01-02 | DTI |  | GREEN
GIT Develop Stage
-90003.5 | 0 | GIT Develop Start | NA | 2014-01-02 | DTI |  | GREEN
-852 | 4 | Implementation Strategy completed | NA | 2014-01-02 | DTI |  | GREEN
-90004 | 1 | GIT Design Start | NA | 2014-01-02 | DTI |  | GREEN
-853 | 3 | Requirements definition completed | NA | 2014-01-02 | DTI |  | GREEN
-854 | 3 | Architecture Description completed | NA | 2014-01-02 | DTI |  | GREEN
-855 | 3 | Mid level platform design completed | NA | 2014-01-02 | DTI |  | GREEN
-499-263 | 3 | Master Work Order - request for quotation issued | NA | 2014-01-02 | DTI |  | GREEN
-499-264 | 3 | Master Test Plan completed | NA | 2014-01-02 | DTI |  | GREEN
-499-265 | 3 | Detailed Platform Application Design baselined | NA | 2014-01-02 | DTI |  | GREEN
-499-266 | 3 | Non-Functional Test Plan drafted | NA | 2014-01-02 | DTI |  | GREEN
-499-267 | 3 | Functional Test Plan completed | NA | 2014-01-02 | DTI |  | GREEN
-90005 | 3 | GIT Design End (IT Readiness Assessment 3.1 signed off) | NA | 2014-01-02 | DTI |  | GREEN
-90006 | 3 | GIT Build Start | NA | 2014-01-02 | DTI |  | GREEN
-499-270 | 3 | ITEC 2 Waiver completed | NA | 2014-01-02 | DTI |  | GREEN
-499-271 | 3 | Non-Functional Test Plan completed | NA | 2014-01-02 | DTI |  | GREEN
-880 | 4 | Implementation Plan completed | NA | 2014-01-02 | DTI |  | GREEN
-499-273 | 4 | Decommissioning Plan finalised | NA | 2014-01-02 | DTI |  | GREEN
-499-274 | 4 | Support Matrix completed | NA | 2014-01-02 | DTI |  | GREEN
-499-275 | 4 | Build Test Report completed | NA | 2014-01-02 | DTI |  | GREEN
-90007 | 0 | GIT Build End | NA | 2014-01-02 | DTI |  | GREEN
-90008 | 1 | GIT Test Start | NA | 2014-01-02 | DTI |  | GREEN
-90009 | 2 | GIT System Test Start | NA | 2014-01-02 | DTI |  | GREEN
-90010 | 1 | GIT System Test End (IT Readiness Assessment 3.2 A signed off) | NA | 2014-01-02 | DTI |  | GREEN
-90011 | 2 | GIT SI Test Start | NA | 2014-01-02 | DTI |  | GREEN
-90012 | 1 | GIT SI Test End (IT Readiness Assessment 3.2 B signed off) | NA | 2014-01-02 | DTI |  | GREEN
-90013 | 2 | GIT UAT Start | NA | 2014-01-02 | DTI |  | GREEN
-90014 | 1 | GIT UAT End | NA | 2014-01-02 | DTI |  | GREEN
-90015 | 2 | GIT NFT Start | NA | 2014-01-02 | DTI |  | GREEN
-90016 | 1 | GIT NFT End | NA | 2014-01-02 | DTI |  | GREEN
-90017 | 2 | GIT OAT Start | NA | 2014-01-02 | DTI |  | GREEN
-90018 | 1 | GIT OAT End | NA | 2014-01-02 | DTI |  | GREEN
-90019 | 2 | GIT Regression Test Start | NA | 2014-01-02 | DTI |  | GREEN
-90020 | 1 | GIT Regression Test End | NA | 2014-01-02 | DTI |  | GREEN
-499-290 | 4 | Non Functional Test Report completed | NA | 2014-01-02 | DTI |  | GREEN
-885 | 4 | End of Test Report completed | NA | 2014-01-02 | DTI |  | GREEN
-499-292 | 0 | All SI Deliverables delivered/complete | NA | 2014-01-02 | DTI |  | GREEN
-890 | 4 | Service Delivery Gateway 1 Approval (+10 days after All SI Deliverables End) | NA | 2014-01-02 | DTI |  | GREEN
-499-294 | 0 | SI Approval for Implementation to proceed (+3 days after SD Gateway 1 Approval) | NA | 2014-01-02 | DTI |  | GREEN
-895 | 4 | SOX Test Stage Review held | NA | 2014-01-02 | DTI |  | GREEN
-90021 | 0 | GIT Test End (IT Readiness Assessment 3.3 signed off) | NA | 2014-01-02 | DTI |  | GREEN
-90021.5 | 0 | GIT Develop End | NA | 2014-01-02 | DTI |  | GREEN
GIT Deploy Stage
-90022 | 0 | GIT Live Start | NA | 2014-01-02 | DTI |  | GREEN
-905 | 4 | Post Implementation Review held | NA | 2014-01-02 | DTI |  | GREEN
-90023 | 0 | GIT Live End | NA | 2014-01-02 | DTI |  | GREEN
-910 | 4 | Implementation completed / Handover Report completed | NA | 2014-01-02 | DTI |  | GREEN
-90024 | 0 | GIT Regulatory Compliance Date | NA | 2014-01-02 | DTI |  | GREEN
-90025 | 1 | GIT SR Decouple Date | NA | 2014-01-02 | DTI |  | GREEN
-90026 | 0 | GIT Warranty End | NA | 2014-01-02 | DTI |  | GREEN
GIT Benefits Stage
-499-307 | 4 | Benefits Delivery Stage | NA | 2014-01-02 | DTI |  | GREEN
-915 | 4 | Benefits Delivery completed / Benefits Delivery Report signed-off | NA | 2014-01-02 | DTI |  | GREEN