## Main
No Projs | 3 | Data
Look ahead | 20 | got
Level | 9999 | Togo
Path | C:\Users\Julian\OneDrive\Documents\OneSheet\titilayo ilesanmi\Planning template v3.1.mpp
Import
Report Settings
1
2
3
4
All
Level
Look Ahead (wks)
Exception Report
Generate
Dependancy Report
Generate
Look Ahead Report
Generate
Clear
PPT Export

## Dependancy Report
Ref | Milestone Name | Donor | Baseline Finish | Forecast Finish | RAG | Last RAG | Issue | Impact | Action | Project
79 | Test Environment Strategy Complete | 5 | FALSE | FALSE |  |  | 2020-08-01 | 2020-05-15 | GREEN | AMBER | Data
6 | Solution Feasibility Report Signed Off | 5 | TRUE | FALSE |  |  | 2020-08-01 | 2026-07-24 | RED | AMBER | Data
7 | Group Compliance Checks Complete | 5 | TRUE | FALSE |  |  | 2020-08-01 | 2026-07-24 | RED | GREEN | Data
8 | CSOC Impact Assessment Complete | 5 | TRUE | FALSE |  |  | 2020-08-01 | 2020-05-15 | GREEN | GREEN | Data
9 | PSOC Impact Assessment Complete | 5 | TRUE | FALSE |  |  | 2020-08-01 | 2026-07-24 | RED | GREEN | Data
11 | Define Complete | 5 | TRUE | FALSE |  |  | 2020-08-01 | 2020-05-15 | GREEN | GREEN | got
13 | Design Start | 11 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-05 | RED | GREEN | got
14 | Full Requirements Definition Signed Off | 11 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-05 | RED | GREEN | got
81 | Mid Level Platform Designs Complete | 11 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-05 | RED | GREEN | got
82 | <Test Phase> Environment and Data Ready for Testing | 11 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-05 | RED | GREEN | got
15 | Design Complete | 11 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-05 | RED | RED | got
16 | Build Start | 11 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-05 | RED | RED | Togo
17 | Build Complete | 11 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-05 | RED | RED | Togo
18 | Test Start | 11 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-05 | RED | RED | Togo
86 | User Acceptance Test Complete | 10 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-20 | RED | RED | Togo
84 | Non-Functional Test Start | 10 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-20 | RED | RED | Togo
83 | Non-Functional Test Complete | 10 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-20 | RED | RED | Togo
19 | Test Complete | 10 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-20 | RED | RED | Togo
20 | Develop Complete | 10 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-20 | RED | RED | Togo
21 | Deploy Start | 10 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-20 | RED | RED | Togo
22 | Deployment Start | 10 | FALSE | FALSE |  |  | 2020-05-01 | 2020-06-20 | RED | RED | Togo
23 | Deployment Live | 10 | FALSE | FALSE |  |  | 2020-05-08 | 2020-06-20 | RED | RED | Togo

## Consolidated Exception Report
Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | Last RAG | RAG | Issue | Impact | Action | Project
Missed Red Milestones
Red Milestones in Future
Amber Milestones
Completed Milestones

## Togo
Temp
Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | RAG | Local RAG | Issue | Impact | Action

## Look Ahead Report (4) (hidden)
Business Milestones

## Look Ahead Report (3) (hidden)
Business Milestones

## Look Ahead Report (2) (hidden)
Business Milestones

## Look Ahead Report (hidden)
Business Milestones