## Main
No Projs | 5 | got
Look ahead | 10 | Togo
Level | 2 | Benue
Path | C:\Users\Julian\OneDrive\Documents\OneSheet\titilayo ilesanmi\Planning template v3.1.mpp | Migration
lumidee
Import
Report Settings
1
2
3
4
All
Level
Look Ahead (wks)
Exception Report
Dependancy Report
Look Ahead Report
Clear
PPT Export

## Dependancy Report
Dependency Log
| Ref | Milestone Name | Level | Dep In | Dep Out | Beneficiary | Donor | Baseline Finish | Forecast Finish | RAG | Last RAG | Issue | Impact | Action | Project
| 13 | Design Start | 11 | 0 | 0 |  |  | 2020-05-01 | 2020-06-05 | RED | GREEN |  |  |  | got
| 14 | Full Requirements Definition Signed Off | 11 | 0 | 0 |  |  | 2020-05-01 | 2020-06-05 | RED | GREEN |  |  |  | got
| 81 | Mid Level Platform Designs Complete | 11 | 0 | 0 |  |  | 2020-05-01 | 2020-06-05 | RED | GREEN |  |  |  | got
| 82 | <Test Phase> Environment and Data Ready for Testing | 11 | 0 | 0 |  |  | 2020-05-01 | 2020-06-05 | RED | GREEN |  |  |  | got
| 15 | Design Complete | 11 | 0 | 0 |  |  | 2020-05-01 | 2020-06-05 | RED | RED |  |  |  | got
| 16 | Build Start | 11 | 0 | 0 |  |  | 2020-05-01 | 2020-06-05 | RED | RED |  |  |  | Togo
| 17 | Build Complete | 11 | 0 | 0 |  |  | 2020-05-01 | 2020-06-05 | RED | RED |  |  |  | Togo
| 18 | Test Start | 11 | 0 | 0 |  |  | 2020-05-01 | 2020-06-05 | RED | RED |  |  |  | Togo
| 86 | User Acceptance Test Complete | 10 | 0 | 0 |  |  | 2020-05-01 | 2020-06-20 | RED | RED |  |  |  | Togo
| 84 | Non-Functional Test Start | 10 | 0 | 0 |  |  | 2020-05-01 | 2020-06-20 | RED | RED |  |  |  | Togo
| 83 | Non-Functional Test Complete | 10 | 0 | 0 |  |  | 2020-05-01 | 2020-06-20 | RED | RED |  |  |  | Togo
| 19 | Test Complete | 10 | 0 | 0 |  |  | 2020-05-01 | 2020-06-20 | RED | RED |  |  |  | Togo
| 20 | Develop Complete | 10 | 0 | 0 |  |  | 2020-05-01 | 2020-06-20 | RED | RED |  |  |  | Togo
| 21 | Deploy Start | 10 | 0 | 0 |  |  | 2020-05-01 | 2020-06-20 | RED | RED |  |  |  | Togo
| 22 | Deployment Start | 10 | 0 | 0 |  |  | 2020-05-01 | 2020-06-20 | RED | RED |  |  |  | Togo
| 23 | Deployment Live | 10 | 0 | 0 |  |  | 2020-05-08 | 2020-06-20 | RED | RED |  |  |  | Togo

## Consolidated Exception Report
Exception Report
Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | Last RAG | RAG | Issue | Impact | Action | Project
Missed Red Milestones
28 | 1 | Deploy Complete | 2020-05-08 | 2020-05-29 | 1417.5 | RED | RED |  |  |  | Togo
27 | 1 | Handover Report Signed Off | 2020-05-08 | 2020-05-29 | 1417.5 | RED | RED |  |  |  | Togo
26 | 1 | Post Implementation Review Signed Off | 2020-05-08 | 2020-06-05 | 1421.875 | RED | RED |  |  |  | Togo
25 | 0 | Customer Impacts Delivered | 2020-05-08 | 2020-06-05 | 1421.875 | RED | RED |  |  |  | Togo
24 | 0 | People Impacts Delivered | 2020-05-08 | 2020-06-05 | 1421.875 | RED | RED |  |  |  | Togo
23 | 10 | Deployment Live | 2020-05-08 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
22 | 10 | Deployment Start | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
21 | 10 | Deploy Start | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
20 | 10 | Develop Complete | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
19 | 10 | Test Complete | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
83 | 10 | Non-Functional Test Complete | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
84 | 10 | Non-Functional Test Start | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
86 | 10 | User Acceptance Test Complete | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
85 | 1 | User Acceptance Test Start | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
88 | 0 | System Integration Test Complete | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
87 | 1 | System Integration Test Start | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
91 | 1 | GIT Change Slot Requested | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
90 | 0 | System Test Complete | 2020-05-01 | 2020-06-20 | 1430.625 | RED | RED |  |  |  | Togo
89 | 1 | System Test Start | 2020-05-01 | 2020-06-05 | 1421.875 | RED | RED |  |  |  | Togo
18 | 11 | Test Start | 2020-05-01 | 2020-06-05 | 1421.875 | RED | RED |  |  |  | Togo
17 | 11 | Build Complete | 2020-05-01 | 2020-06-05 | 1421.875 | RED | RED |  |  |  | Togo
16 | 11 | Build Start | 2020-05-01 | 2020-06-05 | 1421.875 | RED | RED |  |  |  | Togo
15 | 11 | Design Complete | 2020-05-01 | 2020-06-05 | 1421.875 | RED | RED |  |  |  | got
Red Milestones in Future
Amber Milestones
Completed Milestones
250 | 4 | Infrastructure Design Review completed | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Benue
249 | 4 | Initial Requirements Specification signed off | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
248 | 4 | Mid Level Platform Design baselined | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
247 | 4 | SOX Impact Assessment submitted | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
246 | 4 | Master Test Plan created | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
245 | 4 | Implementation Plan drafted | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
244 | 4 | Master Work Order - request for quotation issued | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
243 | 1 | GIT Investigation Start | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
242 | 0 | GIT Engagement End (IT Readiness Assessment 2.1 signed off) | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
241 | 4 | IT Finance Workbook & Investment Appraisal Template signed off | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
240 | 4 | IT Project Management Plan completed | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
239 | 4 | Deliverable Review List updated | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
238 | 4 | Architecture Overview completed | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo

## got
Milestone Report - got
| Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | RAG | Local RAG | Issue | Impact | Action
| 12 | 1 | Develop Start | 2020-05-01 | 2020-06-05 | 1903-11-21 21:00 | GREEN | RED |  |  |  | got

## Togo
Milestone Report - Togo
| Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | RAG | Local RAG | Issue | Impact | Action
| 89 | 1 | System Test Start | 2020-05-01 | 2020-06-05 | 1903-11-21 21:00 | RED | RED |  |  |  | Togo
| 90 | 0 | System Test Complete | 2020-05-01 | 2020-06-20 | 1903-11-30 15:00 | RED | RED |  |  |  | Togo
| 91 | 1 | GIT Change Slot Requested | 2020-05-01 | 2020-06-20 | 1903-11-30 15:00 | RED | RED |  |  |  | Togo
| 87 | 1 | System Integration Test Start | 2020-05-01 | 2020-06-20 | 1903-11-30 15:00 | RED | RED |  |  |  | Togo
| 88 | 0 | System Integration Test Complete | 2020-05-01 | 2020-06-20 | 1903-11-30 15:00 | RED | RED |  |  |  | Togo
| 85 | 1 | User Acceptance Test Start | 2020-05-01 | 2020-06-20 | 1903-11-30 15:00 | RED | RED |  |  |  | Togo
| 24 | 0 | People Impacts Delivered | 2020-05-08 | 2020-06-05 | 1903-11-21 21:00 | RED | RED |  |  |  | Togo
| 25 | 0 | Customer Impacts Delivered | 2020-05-08 | 2020-06-05 | 1903-11-21 21:00 | RED | RED |  |  |  | Togo
| 26 | 1 | Post Implementation Review Signed Off | 2020-05-08 | 2020-06-05 | 1903-11-21 21:00 | RED | RED |  |  |  | Togo
| 27 | 1 | Handover Report Signed Off | 2020-05-08 | 2020-05-29 | 1903-11-17 12:00 | RED | RED |  |  |  | Togo
| 28 | 1 | Deploy Complete | 2020-05-08 | 2020-05-29 | 1903-11-17 12:00 | RED | RED |  |  |  | Togo
| 29 | 1 | Benefits Realisation Start | 2020-05-08 | 2020-05-29 | 1903-11-17 12:00 |  | RED |  |  |  | Togo
| 30 | 1 | Benefits Realisation Complete/Project Closed | 2020-05-08 | 2020-05-29 | 1903-11-17 12:00 |  | RED |  |  |  | Togo
| 233 | 1 | GIT Engagement Start | 2020-05-08 | 2020-05-29 | 1903-11-17 12:00 |  | RED |  |  |  | Togo
| 242 | 0 | GIT Engagement End (IT Readiness Assessment 2.1 signed off) | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo
| 243 | 1 | GIT Investigation Start | 2020-05-08 | 2020-05-29 | 0 |  | COMPLETE |  |  |  | Togo

## Benue
Milestone Report - Benue
| Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | RAG | Local RAG | Issue | Impact | Action
| 251 | 0 | Method of Service Introduction Agreed (i.e. V&E Managed / Project Managed/ Change Managed), SI Acceptance Area Representatives Engaged | 2020-05-08 | 2020-05-29 | 1903-11-17 12:00 |  | RED |  |  |  | Benue
| 255 | 0 | GIT Investigation End (IT Readiness Assessment 2.2 signed off) | 2020-05-08 | 2020-05-29 | 1903-11-17 12:00 |  | RED |  |  |  | Benue
| 257 | 0 | GIT Develop Start | 2020-05-08 | 2020-05-29 | 1903-11-17 12:00 |  | RED |  |  |  | Benue
| 259 | 1 | GIT Design Start | 2020-05-08 | 2020-05-29 | 1903-11-17 12:00 |  | RED |  |  |  | Benue

## Migration
Milestone Report - Migration
| Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | RAG | Local RAG | Issue | Impact | Action
| 276 | 0 | GIT Build End | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 277 | 1 | GIT Test Start | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 278 | 2 | GIT System Test Start | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 279 | 1 | GIT System Test End (IT Readiness Assessment 3.2 A signed off) | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 280 | 2 | GIT SI Test Start | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 281 | 1 | GIT SI Test End (IT Readiness Assessment 3.2 B signed off) | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 282 | 2 | GIT UAT Start | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 283 | 1 | GIT UAT End | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 284 | 2 | GIT NFT Start | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 285 | 1 | GIT NFT End | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 286 | 2 | GIT OAT Start | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 287 | 1 | GIT OAT End | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration
| 288 | 2 | GIT Regression Test Start | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | Migration

## lumidee
Milestone Report - lumidee
| Ref | Level | Milestone Name | Baseline Finish | Forecast Finish | DTI | RAG | Local RAG | Issue | Impact | Action
| 289 | 1 | GIT Regression Test End | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | lumidee
| 292 | 0 | All SI Deliverables delivered/complete | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | lumidee
| 294 | 0 | SI Approval for Implementation to proceed (+3 days after SD Gateway 1 Approval) | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | lumidee
| 296 | 0 | GIT Test End (IT Readiness Assessment 3.3 signed off) | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | lumidee
| 297 | 0 | GIT Develop End | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | lumidee
| 299 | 0 | GIT Live Start | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | lumidee
| 301 | 0 | GIT Live End | 2020-06-05 | 2020-07-10 | 1903-12-13 18:00 |  | RED |  |  |  | lumidee